## Slide 1: CREATE Program: 2019 Transport Chicago June 14, 2019
Notes: Alex

## Slide 2: What is CREATE? Chicago Region Environmental and Transportation Efficiency (CREATE) Program
A $4.6 billion Public-Private Partnership (PPP) designed to improve transportation flow through Chicago
CREATE is a cooperative project involving:
  US Department of Transportation (FHWA & FRA)
  Illinois Department of Transportation (IDOT)
  Cook County
  Chicago Department of Transportation (CDOT)
  6 major North American freight rail carriers and 2 switching railroads
  2 passenger carriers (Amtrak & Metra)
CREATE Partners
Notes: Alex

## Slide 3: Keeping the Nation’s Economy Moving
Notes: Alex

## Slide 4
Four Corridors
  Passenger Corridor
  East-West Corridor
  Beltway Corridor
  Western Ave. Corridor
Notes: Alex

## Slide 5: Project Status
25 road/rail grade separations
6 passenger/freight rail grade separations
Railroad projects to improve rail infrastructure and upgrade technologies
Viaduct improvement program
Grade crossing safety enhancements
Rail operations and visibility improvements
Notes: Alex

## Slide 6: CREATE Program Benefits
Notes:   ALEX
  Passenger train delay reduced by over 1.3 million passenger hours annually
  92,000 hours of truck delay and 230,000 hours of motorist and bus passenger delay will be saved
  200 vehicle crashes with trains will be avoided
  2,800 metric tons/year avoided emissions from idling vehicles
  Enable extra 50,000 freight trains to travel through the greater Chicago rail network annually
  122 million tons of freight per year would travel by rail, avoiding 18,500 truck trips per day on highways

## Slide 7: ON THE MOVE Project Delivery
Notes: Jeff

## Slide 8: Partners Keep CREATE Moving
GRADE SEPARATION STUDIES
Archer Avenue
  Phase I study
Columbus Avenue
Awarded Competitive State Freight Grant ($49 M), June 2018
  Phase III construction is funded, expected timing 2022-2023
95th Street & Eggleston Avenue
  Awarded FRA grant, Phase I in progress
Columbus Ave.
Notes: Jeff - GS highlights

## Slide 9: Partners Keep CREATE Moving
GRADE SEPARATION STUDIES
63rd Street/65th Street & Harlem Avenue (IL43)
Phase I in progress
54th & Central Avenue
Phase I in progress
Notes: Sam – GS highlights

## Slide 10: Partners Keep CREATE Moving
BNSF Connection (WA4)
  Completed
Canal Flyover (P6)
  Phase I documents submitted in 2019
Crossovers Upgrades (B1)
  In construction
Dolton Interlocking (WA11)
  CRISI Grant submitted 2018
B1 signal installation
Notes: Bill - RR proj highlight

## Slide 11: Union Pacific Third Mainline (B2)
Location: Melrose Park, IL
60 freight trains & 59 Union Pacific Metra trains affected
Results
  Constructed 3.5-mile third main track on UP
  Constructed railroad bridge over Addison Creek
  Constructed flyover connection from the Indiana Harbor Belt (IHB) to Union Pacific (UP)
  Control points reconfigured
  Track between the UP and IHB upgraded
  Metra’s Berkeley and Bellwood passenger stations improved; pedestrian underpasses constructed
Before
After
Notes: Bill

## Slide 12: Englewood Flyover (P1)
  Removed conflict point between commuter, passenger and freight trains, alleviating delay for commuters and Amtrak’s most severe delay point in the Midwest.
  Completed 2014
  Reduced rail/rail conflicts
Notes: Bill

## Slide 13: Englewood Flyover (P1)
Before 2011
After 2014
Looking North
Notes: Bill

## Slide 14: Viaduct Program
Locations in the City of Chicago
Improved roadways, sidewalks and drainage under railroad viaducts
Enhanced safety and security for motorists, pedestrians and bicyclists
37 locations completed in 2006
14 locations completed in 2012 (USDOT TIGER funding, $5 million)
11 completed in 2015/2016 (State of Illinois funding)
Notes: Jeff

## Slide 15: Viaduct Improvement Program
Before
After
Example: 1530 S Loomis Street
After
Example: 1530 S Racine Avenue
Before
Notes: Jeff

## Slide 16: INFRA Grant Funded Projects
Notes: Sam

## Slide 17
INFRA Grant Award in 2018
  $474 million total funding commitment will
    Complete design of the entire 75th St. CIP
    Build Argo Connections (B9)
    Build half of 75th St. CIP
$132 million federal INFRA funds closed the funding gap and advances the project toward completion
Due to federal funding requirements projects must meet design and construction schedules
Notes: SAM
Note Federal timeline and implications
Funding Breakdown:
  $116M – Class I RR
  $132M – Federal
  $5M – Amtrak
  $77.75M – Cook County
  $23.75M – Metra
  $8.5M – CDOT
  $111M – IDOT

## Slide 18: INFRA Grant Funded Projects
75th Street CIP (design and partial construction)
Argo Junction (construction)
75th Street CIP (design and partial construction)
Notes: JEFF

## Slide 19: Status of INFRA Grant Funded Projects
Design complete
Contractor selected
Designer selected
Contractor TBD
Designer selected
Contractor TBD
Designer TBD
Construction not yet funded
Designer TBD
Construction not yet funded
Notes: JEFF

## Slide 20: Argo Connections (B9)
Phase III Construction
Selection for Construction Management in progress
CSX responsible railroad
Notes: SAM
Explain force account
B9 is at $36M from CSX request (still needs validation from IDOT), $34M was an old number from the grant
DBE % was assigned by Pam Simon from Central office Dec 2017
Construction observation includes CM to be procured by CSX

## Slide 21: Argo Connections (B9)
Notes: SAM

## Slide 22: A Closer Look at the 75th Street Corridor
I-94
I-57
I-94
I-90
71st
75th
79th
83rd
87th
95th
Pulaski
Kedzie
California
Western
Damen
67th
Ashland
Racine
Halsted
Michigan
King
Columbus
Vincennes
CSX
CSX
Metra RID
Metra RID
UPRR
Metra SWS & NS
BRC
BRC
& NS
NS & Metra
Metra RID
NS
CSX
CSX
Existing Conditions
I-94
I-57
I-94
I-90
71st
75th
79th
83rd
87th
95th
Pulaski
Kedzie
California
Western
Damen
67th
Ashland
Racine
Halsted
Michigan
King
Columbus
Vincennes
CSX
Metra RID
Metra RID
UPRR
Metra SWS & NS
BRC
BRC
& NS
NS & Metra
Metra RID
NS
CSX
CSX
CSX
Railroad Operations
CSX
BRC
NS
UP
Metra
Amtrak
Forest Hill
Junction
Belt Junction
80th St Junction
71st St Grade Crossing
  Trains delayed
  Trains idle on tracks while waiting
Notes: Jeff

## Slide 23: A Closer Look at the 75th Street Corridor
Proposed Conditions
I-94
I-57
I-94
I-90
71st
75th
79th
83rd
87th
95th
Pulaski
Kedzie
California
Western
Damen
67th
Ashland
Racine
Halsted
Michigan
King
Columbus
Vincennes
CSX
CSX
Metra RID
Metra RID
UPRR
Metra SWS & NS
BRC
BRC
& NS
NS & Metra
Metra RID
NS
CSX
CSX
Railroad Operations
CSX
BRC
NS
UP
Metra
Amtrak
EW2
80th St Junction Reconfiguration
P2
Rock Island Connector
(untangles Belt Junction)
P3
Forest Hill Flyover
GS19
71st St Grade Separation
  Fluid train movement
  Trains pass through without idling
Notes: Jeff

## Slide 24: What will the current funding do?
I-94
I-57
I-94
I-90
71st
75th
79th
83rd
87th
95th
Pulaski
Kedzie
California
Western
Damen
67th
Ashland
Racine
Halsted
Michigan
King
Columbus
Vincennes
CSX
CSX
Metra RID
Metra RID
UPRR
Metra SWS & NS
BRC
BRC
& NS
NS & Metra
Metra RID
NS
CSX
CSX
Railroad Operations
CSX
BRC
NS
UP
Metra
Amtrak
GS19
71st St Grade Separation
GS19
Design
Construction
The CREATE Partners will seek future funding to finish construction of P2 and EW2.
P3
Forest Hill Flyover
P3
P2
Rock Island Connector
(untangles Belt Junction)
P2
EW2
80th St Junction Reconfiguration
EW2
Notes: Jeff

## Slide 25
P3 - Forest Hill Flyover
Construct bridge to carry north-south CSX tracks over east-west tracks at 75th Street and over roadway at 71st Street
Bridge extends from 68th Street to 79th Street
Existing Conditions, facing east
Concept Rendering, facing east
Notes: Jeff

## Slide 26
P3 - Forest Hill Flyover
Existing Cross-Section, facing north
Approx. 130 ft.
New CSX Railroad Bridge over Metra, BRC & NS – 7500S to 7900S
Approx. 110 ft.
Approx. 40 ft.
Property Line
Max 30 ft.
Temporary CSX Tracks
(while bridge is being built)
Conceptual Cross-Section, facing north
Property Line
Notes: Jeff

## Slide 27
GS19 - 71st St. Grade Separation
Separates 71st Street and the north-south CSX tracks
Between Hamilton Avenue and Bell Avenue, north of Forest Hill Junction
Concept Rendering, facing west
Existing Conditions, facing west
Notes: Jeff

## Slide 28: Status of Forest Hill Junction (P3) & 71st St. Grade Separation (GS19)
Phase II Design – Parsons Team Selected
CSX Responsible Railroad
DBE % Assigned: 30%
IDOT Notice to Advertise: January 2019
Solicit RFP: February 2019
Selection: April 2019
Design Start: Summer 2019*
Design Completion: Spring 2021*
Design scope: Project management, structure and civil design, track design and railway signal design
*Anticipated timing
Notes: Sam

## Slide 29: Status of Forest Hill Junction (P3) & 71st St. Grade Separation (GS19)
Phase III Construction – Contractor TBD
CSX Responsible Railroad
DBE % Assigned: TBD
Construction sequence: Subject to change
  Temporary civil and track construction (shoofly)
  Permanent structure, grade separation, track and signal construction
IDOT Notice to Advertise (temporary construction): Spring 2020*
Solicit Bids (temporary construction): Spring 2020*
Bid and award: Summer 2020* (temporary construction)
Temporary Construction: Summer 2020 – Summer 2021*
IDOT Notice to Advertise (Permanent): Summer 2021
Permanent construction: Winter 2022 - Fall 2024*
*Anticipated timing
Notes: SAM

## Slide 30
Viaduct Improvements
in the P3-GS19 project area
  Reconstruction of streets and sidewalks under existing structures
  Replacement of viaduct lighting
  Similar improvements made in the area during 2012 and 2015
Example of viaduct improvement completed by CDOT during 2015: 600-700 W. 80th Street
Street & sidewalk
before 2015 CDOT improvements
Street & sidewalk after 2015 CDOT improvements
Notes: Jeff

## Slide 31
Community Mobility Improvements
Sidewalk improvements
Street improvements
Bus stop improvements
New street trees
Bicycle facilities
Notes: Jeff

## Slide 32: Status of Viaduct and Community Mobility Improvements
Design & Construction
IDOT/CDOT Responsible Agencies
DBE % Assigned: Varies by project; most of these types of improvements will be built to spec (i.e., new sidewalks, drainage, paving, lighting, trees, etc.)
CDOT Notice to Advertise: Winter 2020*
Solicit Bids: Spring 2020*
Construction start: 2020 – 2021*
Construction completion: 2021 – 2022*
Bid scope: Varies by project (i.e., new sidewalks, drainage, paving, lighting, trees, etc.)
*Anticipated timing
Notes: JEFf

## Slide 33: What will the current funding do?
I-94
I-57
I-94
I-90
71st
75th
79th
83rd
87th
95th
Pulaski
Kedzie
California
Western
Damen
67th
Ashland
Racine
Halsted
Michigan
King
Columbus
Vincennes
CSX
CSX
Metra RID
Metra RID
UPRR
Metra SWS & NS
BRC
BRC
& NS
NS & Metra
Metra RID
NS
CSX
CSX
Railroad Operations
CSX
BRC
NS
UP
Metra
Amtrak
GS19
71st St Grade Separation
GS19
Design
Construction
The CREATE Partners will seek future funding to finish construction of P2 and EW2.
P3
Forest Hill Flyover
P3
P2
Rock Island Connector
(untangles Belt Junction)
P2
EW2
80th St Junction Reconfiguration
EW2
Notes: JEFF

## Slide 34
P2 - Rock Island Connector
New Metra flyover structure south of Hamilton Park
Proposed path of structure and land use map from 2014 Environmental Impact Statement report
Notes: JEFF

## Slide 35
P2 - Rock Island Connector
Emerald Ave
Proposed Metra tracks on new structure above
Freight railroad tracks realigned on existing embankment
Union Avenue underpass to be removed & embankment widened to south
Notes: JEFF

## Slide 36: Status of Rock Island Connector (P2)
Phase II Design
Metra Responsible Railroad
  Hire Design consultant: Summer 2019*
  DBE % will be assigned
  IDOT involved with selection process
PS&E submittal: Summer 2021*
State Rail Agreements
Funding for construction needed
*Anticipated timing
Notes: SAM

## Slide 37
EW2 – Belt Jct. & 80th St. Jct. Reconfiguration
Track realignment and reconstruction of existing railroad structures
EW2
80th St Junction Reconfiguration
Project Area
Notes: BILL

## Slide 38: Status of Belt Jct. & 80th St. Jct. Reconfiguration (EW2)
Phase II Design
Belt Junction & 80th Street Junction (EW2)
  Norfolk Southern Responsible Railroad
    Hire lead consultant: Summer 2019
    Hire design consultant: Fall 2019*
    DBE % will be assigned
    IDOT involved with selection process
  PS&E submittal: Summer 2021*
  State Rail Agreements
*Anticipated timing
Villa Grove Subdivision (EW2)
  Union Pacific Responsible Railroad
    Hire Design Consultant: Summer 2019*
    DBE % will be assigned
    IDOT involved with selection process
  PS&E submittal: Summer 2021*
  State Rail Agreements
Notes: BILL

## Slide 39: Timeline
Notes: BILL

## Slide 40: CREATE Bid Advertisements/RFPs
Sign-up at createprogram.org/business.htm
Receive each partner’s CREATE Bid Advertisements
Notes: SAM

## Slide 41: Thank You! Questions?
E-mail: info@createprogram.org
Procurement Sign Up: www.createprogram.org/business.htm
“Like” Us on Facebook at:
Facebook.com/CREATEProgramChicago
Notes: SAM